## SEARCH
State | Owner | Contacted | Responded | Existing Mapping | Mapping Received | Mapping Vetted | Mapping Created | Contact Name | Notes
Alabama | SEARCH | 2018-01-02 | 2018-01-05 | Yes | Yes |  |  | David Urquhart | need to create mapping
Alaska | SEARCH | 2018-01-02 | 2018-01-03 | Yes | Yes |  |  | Kathy Monfreda | Alaska's Uniform offense Citation Table
Arizona | SEARCH | 2018-01-02 | [5 empty] | Lt. Col. Timothy Chung | Mike contacted on 3/13, LtCol Chung assigned staff to fulfill the request
Arkansas | SEARCH | 2018-01-02 | 2018-01-03 | Yes | Yes |  |  | Ralph Ward
California | SEARCH | 2018-01-02 | 2018-01-30 | No |  |  |  | Keith Dann | need to create mapping
Colorado | SEARCH | 2018-01-02 | [5 empty] | Chris Andrist | Mark to contact
Connecticut | SEARCH | 2018-01-02 | [5 empty] | Michael Lawlor | Mike contacted on 3/13
Delaware | SEARCH | 2018-01-02 | [5 empty] | David Elwood | Mark conntaced on 3/13, Mr. Elwood responded with an example tool - 3/16 - Mike asked for tables
Florida | SEARCH | 2018-01-02 | 2018-01-04 | Yes | Yes |  |  | Charlie Schaeffer
Georgia | SEARCH | 2018-01-02 | 2019-03-16 | No |  |  |  | Cheryl Payton | Mike contacted on 3/15, need to create mapping
Hawaii | SEARCH | 2018-01-02 | [5 empty] | Chris Young | Becki contacted on 3/13
Idaho | SEARCH | 2018-01-02 | 2018-02-02 | Yes | Yes |  |  | Dawn Peck | only statute and NCIC code included in table (not very accurate mappings)
Illinois | SEARCH | 2018-01-02 | 2018-01-03 | No |  |  |  | Captain John Rattigan | need to create mapping
Indiana | SEARCH | 2018-01-02 | 2018-01-04 | No |  |  |  | FSgt. Jon Carmin | need to create mapping
Iowa | SEARCH | 2018-01-02 | 2018-01-05 | Yes | Yes |  |  | David Jobes | Charge code application in Iowa: http://165.206.16.55/chargecode/gov.iowa.dhr.cjis.cca.CCA/CCA.html
Kansas | SEARCH | 2018-01-02 | 2018-01-09 | Yes | Yes |  |  | Leslie Moore
Kentucky | SEARCH | 2018-01-02 | 2018-02-06 | No |  |  |  | Brandon Cobb / Lt. Col. Jeff Medley | need to create mapping
Maine | SEARCH | 2018-01-02 | [5 empty] | Matt Ruel | 3/15/18 Andrew talking to Matt
Maryland | SEARCH | 2018-01-02 | 2018-01-30 | No |  |  |  | Robyn Lyles | need to create mapping
Massachusetts | SEARCH | 2018-01-02 | [5 empty] | Curt Wood | Becki contacted on 3/13 - Mr. Wood is following up
Michigan | SEARCH | 2018-01-02 | 2018-02-02 | Yes | Yes |  |  | Katie Bower
Minnesota | SEARCH | 2018-01-02 | 2018-01-07 | Yes | Yes |  |  | Dana Gotz/Patrici Zafke
Missouri | SEARCH | 2018-01-02 | 2018-01-30 | No |  |  |  | Major David Flannian | interested in assistance with mapping - need to create mapping
Montana | SEARCH | 2018-01-02 | 2018-01-08 | Yes | Yes |  |  | Jason Bright
Nebraska | SEARCH | 2018-01-02 | 2018-01-30 | Yes | Yes |  |  | Tony Loth
Nevada | SEARCH | 2018-01-02 | 2018-01-31 | Yes | Yes |  |  | Julie Butler
New Hampshire | SEARCH | 2018-01-02 | 2018-03-14 | No |  |  |  | Jeff Kellett | Mike contacted on 3/13 - no state mappings to NCIC codes
New Jersey | SEARCH | 2018-01-02 | 2018-03-13 | Yes | Yes |  |  | Brandon Gray | Maping received after Becki followed up on 3/13
New York | SEARCH | 2018-01-02 | 2018-01-12 | Yes | Yes |  |  | Adam Dean | interested in the sustainability discussions
North Carolina | SEARCH | 2018-01-02 | 2018-01-30 | No |  |  |  | Ashley Cox | interested in assistance with mapping - need to create mapping
North Dakota | SEARCH | 2018-01-02 | 2018-01-19 | Yes | Yes |  |  | Molly Goebel | The ND common statute table is online at: https://attorneygeneral.nd.gov/criminal-justice-resources/common-statute-table
Ohio | SEARCH | 2018-01-02 | 2018-03-13 | No |  |  |  | Rickeya Franklin | Becki followed up on 3/13 - no mapping available
Oklahoma | SEARCH | 2018-01-02 | 2018-01-04 | No |  |  |  | Bryan Rizzi / Gene Thaxton | need to create mapping
Pennsylvania | SEARCH | 2018-01-02 | 2018-01-09 | No |  |  |  | Bob Merwine | need to create mapping
Puerto Rico | SEARCH | 2018-01-02 | 2018-01-15 | Yes | Yes |  |  | Eduardo Cancel-Maldonado
South Carolina | SEARCH | 2018-01-02 | 2018-01-12 | Yes | Yes |  |  | Major Jennie Temple
South Dakota | SEARCH | 2018-01-02 | [5 empty] | Chad Mosteller | Mike contacted on 3/13
Tennessee | SEARCH | 2018-01-02 | [5 empty] | Brad Truitt | Becki contacted on 3/13
Texas | SEARCH | 2018-01-02 | 2018-01-03 | Yes | Yes |  |  | Mike Lesko
Utah | SEARCH | 2018-01-02 | 2018-01-31 | Yes | Yes |  |  | Sam Clark
Vermont | SEARCH | 2018-01-02 | [5 empty] | Jeff Wallin | 3/15/18 Andrew talking to VT CCH
Virginia | SEARCH | 2018-01-02 | 2018-01-30 | No |  |  |  | Captain Tricia Powers | interested in assistance with mapping - need to create mapping
Washington | SEARCH | 2018-01-02 | 2018-01-04 | No |  |  |  | Jim Anderson | need to create mapping
Wyoming | SEARCH | 2018-01-02 | 2018-01-02 | No |  |  |  | Eric Wiltanger | need to create mapping
District of Columbia | Nlets | 2018-01-12 | [5 empty] | Melanie Nathan/Mannone Butler | Becki contacted Mannone Butler (SEARCH member) and Ms. Butler is following up on the request
Guam | Nlets
Louisiana | Nlets | 2018-01-11 | X | [5 empty] | Doesn't currently exist but LA looking to build mapping
Mississippi | Nlets | 2018-01-12 | [5 empty] | Lt. Charlie Hill
New Mexico | Nlets | 2018-01-31 | X | Hopefully |  |  |  | Tim Struck | Tim believes that NM has a table. He is looking into this and will get back to Kate ASAP.
Oregon | Nlets | 2018-01-12 | [5 empty] | Steve Hathaway
Rhode Island | Nlets | 2018-01-12 | X |  |  |  |  | Linda Fraccola, Ed Cabral | NIBRS provided. No NCIC mapping available. Ed Cabral is going to see if he can perform the mapping for us
Virgin Islands | Nlets
West Virginia | Nlets | 2018-01-12 | X | X |  |  |  | Chris Behre
Wisconsin | Nlets | 2018-01-12 | X | X |  |  |  | Walt Neverman/Katie Schuh